2678 HOLDINGS LLC

TokenCap Miner LLC (TCM)

Build Workplan — June 30 Controlled Pilot Launch

Revised v3 — F2: client intake portal added · F4–F8: managed risk and open items corrected · F13: patent owner assigned

| Field | Value |
| --- | --- |
| Document ID | TCM-BUILD-009 v3 |
| Version | 1.0 — June 2026 |
| Classification | Internal — Privileged & Confidential |
| Owner | 2678 Holdings LLC — Managing Member |
| Supersedes | TCM-BUILD-009 v2 |
| Launch target | June 30, 2026 (Day 26) |
| TCM Technology Lead | Stan |
| TCN Technology Lead | Ganlin |
| Patent-alignment owner | Stan — reviews all APIs and features against 40 patent claims before production deployment |

PRIVILEGED & CONFIDENTIAL  ·  INTERNAL USE ONLY  ·  2678 Holdings LLC

# I. PILOT SCOPE — WHAT SHIPS JUNE 30

| Component | Ships June 30 | Notes |
| --- | --- | --- |
| TCTCredential.sol on Polygon PoS mainnet | YES | Non-upgradeable. Transfer hooks reverted. Fuzz-tested. |
| TCTOutcomeRegistry.sol on Polygon PoS mainnet | YES | UUPS proxy behind timelock (timelock duration: Stan decides by Day 2). |
| AWS ECS Fargate + 2× RDS PostgreSQL (TCM-dedicated account) | YES | ECS Fargate for pilot (not EKS — see managed risk F4). EKS in v1.1. |
| Persona KYC — real identity verification | YES | Pilot KYC vendor. JPM = config swap when contract closes. Zero code change. |
| Six issuance gates (Gates 1–5) | YES | Gate 6 (escrow) deferred — no project listings in pilot. |
| Auth API (TCM-CRED-VERIFY-002) with mTLS | YES | Schema LOCKED. Stan + Ganlin co-signed. |
| Append-only audit log with hash-chain | YES | Inter-entity event ingestion deferred to v1.1. |
| F2 NEW — Client intake portal (simulated data) | YES | Participant-facing onboarding UI. Full 6-gate flow with simulated data for non-live fields. Real Persona KYC. Real wallet binding. Real mint and activation. Simulated project listings and lister context where live data not yet available. Replaces admin-only onboarding. |
| Admin portal (Next.js) — credentials, status management | YES | Internal-facing credential management. Separate from client intake portal. |
| 5–10 pilot participants — real KYC, real wallets, real tokens | YES | Processed through client intake portal. |
| JPMorgan Chase KYC | NO — DEFERRED | Contract in negotiation. Persona handles pilot. JPM = config swap. |
| CloudHSM signing key custody | NO — MANAGED RISK | AWS KMS for pilot. See managed risk table. |
| External smart contract audit | NO — MANAGED RISK | 8–16 week lead time. Being booked in parallel. |
| TCM-TOKEN-STATE-005 | NO — PATENT GATE | Non-waivable. Stan reviews first, then Legal confirmation required. |
| Full sync pipeline + finality state machine | NO — DEFERRED | v1.1. Sync pipeline question deferred per MRB June 4, 2026. |
| Project lister live portal | NO — DEFERRED | Lister context simulated in client intake portal for pilot. Full lister portal in v1.1. |

# II. MANAGED RISK ACKNOWLEDGEMENT — MRB SIGN-OFF REQUIRED BEFORE DAY 1

MRB must sign this table before any code is written. Five trade-offs authorised for the June 30 pilot scope. All are bounded, documented, and reversible in v1.1.

| # | Trade-off | What it means | Production spec being departed from | v1.1 upgrade |
| --- | --- | --- | --- | --- |
| 1 | Persona instead of JPMorgan Chase | Real KYC — not simulated. Persona is a production vendor. JPM = Secrets Manager config change only (endpoint + API key). Zero code change. | TCM Tech Specs v2 Part VI | JPM contract in negotiation. Swap in when signed. |
| 2 | AWS KMS instead of CloudHSM | AWS KMS is managed HSM-backed. Adequate security for 5–10 participant pilot. Difference is dedicated vs. shared hardware. | TCM Tech Specs v2 Part VIII: 'AWS CloudHSM, minimum 2 HSM instances per cluster for HA' | CloudHSM cluster provisioned in v1.1. |
| 3 | No external smart contract audit before pilot | Internal Foundry fuzz tests cover all transfer-disable paths. Audit (Trail of Bits / ConsenSys) being booked in parallel — 8–16 week lead time. | API Policy §4.3 pre-production security testing requirements for Critical APIs | Audit completes before v1.1 full production launch. |
| 4 (F4 NEW) | ECS Fargate instead of EKS | ECS Fargate is faster to provision for pilot scale. Production requires EKS for multi-AZ auto-scaling and 99.9% SLA. | TCM Tech Specs v2 Part VIII: 'Amazon EKS, m6i.xlarge, min 2/max 8 nodes, Multi-AZ' | Migrate to EKS in v1.1 before production scale. |
| 5 | Direct event polling instead of full sync pipeline | Polling Polygon PoS events directly is sufficient for 5–10 participants. Full finality state machine is over-engineered for pilot scale. | TCM Tech Specs v2 Part II (Seven-layer system, Event Layer + Sync) | Full sync pipeline built in v1.1. |

# III. OPEN ITEMS — FORMALLY CLOSED (PILOT SCOPE DECISIONS)

F8 FIX: Open Items from TCM Tech Specs v2 Part XII that require MRB sign-off to formally close.

| Open Item | Pilot-scope decision | v1.1 production decision | Closed by |
| --- | --- | --- | --- |
| Open Item 1: Canonical event serialization format (Protobuf vs JSON with sorted keys) | F6 FIX: JSON with deterministic key ordering (alphabetically sorted keys). Recommended by Stan as the senior engineering call for the 26-day timeline. Protocol Buffers deferred to v1.1 for determinism guarantees. | Protocol Buffers for v1.1 sync pipeline. Normalizer rewrite with Protobuf at v1.1. | Stan sign-off as senior engineer required before normalizer is coded (Sprint Day 4–5) |
| Open Item 2: Credential expiry/renewal policy | expiry_policy_months = 0 (no expiry) for pilot. Chain registry config parameter added. No renewals in 5–10 person pilot. | MRB to confirm final expiry policy before first production cohort is minted. | MRB confirms as part of this sign-off package |
| Open Item 3: Ethereum mainnet anchoring cadence | Not in pilot scope — no anchoring infrastructure in pilot. | Monthly anchoring cadence (single tx per commit). MRB to confirm. | Deferred to v1.1 |
| Open Item 4: Multi-sig thresholds per role | Single AWS KMS key per role for pilot (ISSUER_ROLE, REVOCATION_ROLE_TCM, PAUSER_ROLE). Multi-sig not feasible in 26-day timeline. | DEFAULT_ADMIN_ROLE: 3-of-5. REVOCATION_ROLE_TCM: 2-of-3. PAUSER_ROLE: 2-of-3. MRB confirms thresholds. | MRB confirms as part of this sign-off package |
| Open Item 5: Contract upgrade model | TCTCredential: non-upgradeable. TCTOutcomeRegistry: UUPS proxy behind timelock (timelock duration: Stan recommends by Day 2 of sprint). | Same model carries to production. | Stan confirms timelock duration by Sprint Day 2 |
| Open Items 6–7: JPM contract + audit firm | JPM: initiate contact this week. Audit: book Trail of Bits or ConsenSys this week. | Both required before v1.1 production launch. | MRB initiates both this week |
| Open Item 8: TCA/analytics entity structure | Analytics feed API stubbed — emits feed-shaped records from day one per MRB direction. TCA entity structure resolved in patent project. | Analytics Feed Store populated. TCA integration when entity structure confirmed. | Per MRB: resolved in patent project |
| Open Item 9: Gas markup final percentage | 20% placeholder in chain registry config. No billing goes live in pilot. | MRB confirms final rate before billing goes live (v1.1 Month 6). | Deferred to v1.1 |
| Open Item 10: Runbooks | 4 runbooks (mTLS rotation, RPC failover, SDN kill switch, Auth API outage) written by Sprint Day 21. Tabletop tested before launch. | Full 10-runbook set for v1.1. | Stan assigns one engineering owner per runbook. Drafting Month 4 of v1.1. |

# IV. F2 — CLIENT INTAKE PORTAL SPECIFICATION

MRB decision June 4, 2026: add client intake portal to pilot scope. Full 6-gate onboarding flow with simulated data where live data is not yet available. Real KYC, real wallet binding, real mint, real activation. Project context simulated.

## What the client intake portal is

The client intake portal is the participant-facing onboarding surface. It is distinct from the admin portal (staff-facing credential management). In the June 30 pilot it handles the participant journey from initial intake through credential activation.

| Portal screen | Content in pilot | Live vs simulated |
| --- | --- | --- |
| Landing / intake form | Participant name, email, jurisdiction selection, credential class (0x0001 base) | Live — real data collected |
| Eligibility check (Gate 1) | Display eligibility criteria for the credential class. Eligibility confirmation. | Simulated — lister criteria are stub values in the pilot. Real logic in v1.1 when live project listings exist. |
| Identity verification (Gate 2) | KYC intake form → Persona API → verification result displayed | LIVE — real Persona KYC. Real identity verification. Real jurisdiction code returned. |
| Wallet binding (Gate 3) | Wallet connection (MetaMask or similar). Ownership challenge. Signing flow. | LIVE — real wallet. Real EIP-191/EIP-1271 signature verification. Real identity_binding hash computed. |
| Mint confirmation (Gate 4) | Display pending token information. Confirm mint transaction submitted to Polygon PoS mainnet. | LIVE — real ISSUER_ROLE mint on Polygon PoS mainnet. Real token_id assigned. |
| Activation confirmation (Gate 5) | Display active credential. Token ID, status, jurisdiction, activated_at timestamp. | LIVE — real activation. isAuthorized = true on-chain and in credential_state_mirror. |
| Credential dashboard | Credential status, audit activity log. Outcome references panel shows placeholder content (no live sync pipeline). | PARTIALLY LIVE — credential status and audit log are live. Outcome references simulated pending sync pipeline (deferred per F3 discussion). |
| Project listings (context) | Browse-mode display of project types and credential utility. No live lister-submitted projects. | SIMULATED — static content describing credential use cases. Live project listings in v1.1 when lister portal is built. |

## Client intake portal build tasks

- Sprint Days 9–13: Next.js client intake portal. Separate from admin portal. Mobile-responsive. Gates 1–5 wired to real backend APIs.

- Sprint Day 13: Simulated project context pages. Static content. No real lister accounts.

- Sprint Day 15: First real participants processed through the client intake portal (not admin-only onboarding).

- Sprint Day 25: Dress rehearsal includes a new participant completing the full client intake portal flow end-to-end.

# V. SPRINT PHASES

| Phase | Days | Focus | Gate |
| --- | --- | --- | --- |
| Phase 1 — Decisions & Infrastructure | 1–3 | Lock all open items. Provision AWS. Deploy to Amoy testnet. Stan confirms timelock duration for TCTOutcomeRegistry. | MRB signs managed risk acknowledgement (5 items) · Stan + Ganlin co-sign Auth API schema |
| Phase 2 — Core Build | 4–10 | Smart contract, DB, KYC module, gates 1–5, Auth API, event listener. | MRB sign-off: full stack running on Amoy testnet |
| Phase 3 — Mainnet + Integration | 11–17 | Deploy to Polygon PoS mainnet. TCN integration live. 3 real participants. OWASP security review. | Ganlin: TCN integration confirmed · MRB: 3 real credentials verified |
| Phase 4 — Pilot Cohort & Hardening | 18–23 | Full cohort (5–10). Client intake portal live. Load test. Failover test. Runbooks. Production mTLS certs. | Ganlin: failover co-sign · MRB: runbooks signed · Pre-launch review |
| Phase 5 — Launch | 24–26 | Buffer, dress rehearsal, final sign-off, go-live June 30. | MRB: final launch authorization |

# VI. PATENT-ALIGNMENT OWNER — ASSIGNED

F13 FIX: Stan assigned as patent-alignment engineering owner per TCM Tech Specs v2 Part I requirement. Non-provisional patent filing deadline: May 2027. Stan reviews every API specification and new feature for patent consistency before production deployment. Stan's review is required before Legal/Compliance issues any written patent confirmation.

| Patent-alignment engineering owner | Stan (TCM Technology Lead) |
| --- | --- |
| Role | Reviews all TCM APIs, smart contract code, and new features against the 40 patent claims across 9 families |
| Authority | Required reviewer before any API specification or feature goes to Legal/Compliance for patent confirmation |
| Non-negotiable review gates | TCM-TOKEN-STATE-005 production deployment · Any new token utility · Any smart contract change · Any API specification change |
| Deadline context | Non-provisional patent filing: May 2027. All build work between June 2026 and May 2027 is in the patent window. |

2678 Holdings LLC  ·  TokenCap Miner LLC  ·  TCM-BUILD-009 v3 — June 2026  ·  June 2026  ·  PRIVILEGED & CONFIDENTIAL