TOKENCAP ADVISORS LLC

R&I Reference Engine

Technology Work Plan

Document ID: TCA-WORKPLAN-2026-RI-001

Prepared By: MRB, Principal — 2678 Holdings LLC

Date: May 2026

Status: DRAFT — Pending MRB Approval

Oversight: Stan Hua, Senior Technology Advisor

# 1. Executive Summary

This work plan scopes the design, build, and deployment of the TCA R&I Reference Engine — a Retrieval-Augmented Generation (RAG) knowledge system providing TokenCap Advisors' Research & Intelligence function with authoritative, auditable geological and technical reference material for E&P project evaluation.

The R&I Reference Engine is a discrete system, separate from the TCA Risk Engine, though designed with a documented integration interface for future data exchange. It addresses a core R&I workflow need: when evaluating operator-submitted project data, analysts require reliable independent reference benchmarks — formation-level type curves, basin production data, geological characterization — to identify material variances and support defensible investment conclusions.

The system will be built using Claude as the primary development resource, supported by a Senior Systems Engineer on a part-time contracting basis, consistent with the 2678 Holdings technology delivery model. Total estimated external cost is approximately $34,500 in SE contractor fees plus ongoing infrastructure costs of $800–$2,000 per month, making this a fraction of the $437,000 Snowflake Professional Services proposal reviewed in December 2025.

# 2. Strategic Context & Problem Statement

## 2.1  The R&I Reference Problem

TCA's R&I workflow requires analysts to evaluate operator-submitted data — geological interpretations, production forecasts, reserve estimates — against authoritative independent benchmarks. Today this is done manually: analysts locate relevant USGS publications, SPE papers, state geological survey data, or EIA production statistics and compare them against operator claims. This process is:

- Time-intensive: locating, reading, and synthesizing reference material for a single project can take 4–8 analyst hours

- Inconsistent: different analysts use different sources, reducing comparability across project evaluations

- Difficult to audit: the reference material underlying an R&I conclusion is rarely systematically documented

- Unscalable: as TCN's project pipeline grows, the manual reference burden grows linearly

## 2.2  What the R&I Reference Engine Is

The R&I Reference Engine is a curated, indexed knowledge corpus of authoritative E&P geology and technical reference material, queryable via natural language. When an R&I analyst submits a question or uploads an operator document, the system retrieves the most relevant authoritative reference content and synthesizes a structured comparison, with full source citations.

Critically, this is not a fine-tuned or custom-trained model. It is a RAG system — the corpus is stored as retrievable, auditable documents; the reasoning is performed by Claude at inference time. This architecture is superior for the R&I use case because every source is traceable, the corpus can be updated without retraining, and the system is explainable by design.

## 2.3  Relationship to the TCA Risk Engine

The R&I Reference Engine is a separate project from the TCA Risk Engine (TCA-WORKPLAN-2026-RE-001). The two systems serve different functions in the workflow: the Risk Engine scores and grades projects against TCA's five-domain risk framework; the Reference Engine provides the geological and technical reference grounding that informs the risk assessment. A documented API integration stub (Task 3.4) will be built in Phase 3 to enable future data exchange between systems.

# 3. Technical Architecture Overview

## 3.1  System Components

The R&I Reference Engine consists of four layers:

Corpus Layer: curated authoritative documents (PDFs, structured data exports, API feeds) from USGS, SPE, state geological surveys, EIA, basin study repositories, and formation-specific production databases. Documents are tagged with metadata: source, domain category, formation/basin, publication date, and reliability tier (Tier 1 = primary government/academic; Tier 2 = industry standard; Tier 3 = operator/secondary).

Ingestion & Indexing Layer: automated pipeline that acquires, normalizes, chunks, and embeds documents into a vector database. Chunking strategy is geology-aware — section boundaries, figure captions, and table data are treated as distinct retrieval units. Embeddings are generated via a selected embedding model (final selection in Phase 1 architecture review).

Retrieval & Synthesis Layer: when a query is submitted, the system retrieves the top-k most relevant corpus chunks via semantic similarity search. Claude receives the query and retrieved chunks and synthesizes a structured reference response with inline citations and a variance analysis if operator data is provided.

Interface Layer: a lightweight web application where R&I analysts submit queries, upload operator documents for comparison, and receive structured reference outputs. Outputs include: reference answer, supporting source citations with drill-down, and a variance flag table when operator claims are present.

## 3.2  Build Model

Claude serves as the primary development resource: application architecture, retrieval logic design, prompt engineering, code generation (Python, API layer, front-end), and quality testing. The Senior Systems Engineer handles infrastructure provisioning, vector database administration, security configuration, deployment pipeline, and knowledge transfer. MRB functions as product owner; Stan provides cross-entity technical oversight.

# 4. Project Work Plan

Total project duration: 20 weeks across 4 phases. All task IDs reference this document (TCA-WORKPLAN-2026-RI-001).

| ID | Task | Description | Owner | Effort |
| --- | --- | --- | --- | --- |
| Phase 1: Foundation & Corpus Planning ¦ Weeks 1–3 |  |  |  |  |
| 1.1 | Source Inventory & Rights Assessment | Catalog authoritative E&P geology sources (USGS, SPE, state geological surveys, basin studies, EIA, formation databases). Assess licensing, format, and access for each. | MRB + SE | 24 hrs |
| 1.2 | Architecture Design | Define RAG stack: vector database selection (pgvector / Chroma / Weaviate), embedding model, chunking strategy, API interface spec. Claude drives design; SE reviews. | Claude + SE | 16 hrs |
| 1.3 | Infrastructure Provisioning | Stand up cloud hosting environment, vector DB instance, document storage (S3 or equivalent), and CI/CD pipeline for corpus updates. | SE | 20 hrs |
| 1.4 | Phase 1 Milestone Review | MRB approval of source inventory, architecture diagram, and hosting plan before build begins. | MRB | 4 hrs |
| Phase 2: Corpus Ingestion & Indexing ¦ Weeks 4–8 |  |  |  |  |
| 2.1 | Document Acquisition Pipeline | Build automated ingestion pipeline: PDF/text acquisition, format normalization, metadata tagging (source, domain, formation, date, reliability tier). | Claude + SE | 32 hrs |
| 2.2 | Chunking & Embedding | Implement domain-aware chunking logic (geology documents require section-aware splitting). Generate embeddings via selected model. Index into vector DB. | Claude + SE | 24 hrs |
| 2.3 | Initial Corpus Load — Tier 1 Sources | Ingest highest-priority authoritative sources: USGS National Assessment data, SPE formation-specific papers, Cotton Valley basin studies, EIA production data. | SE | 20 hrs |
| 2.4 | Retrieval Quality Testing | Test retrieval accuracy against known E&P queries. Tune chunk size, overlap, and similarity thresholds. Minimum: 10 representative R&I query scenarios. | Claude + SE | 16 hrs |
| 2.5 | Phase 2 Milestone Review | MRB and Ganlin validation of retrieval quality against sample R&I queries before proceeding to interface build. | MRB + Ganlin | 4 hrs |
| Phase 3: R&I Interface Build ¦ Weeks 9–14 |  |  |  |  |
| 3.1 | Query Interface — Core | Build web-based query interface: R&I analyst submits question or uploads operator document; system retrieves relevant corpus chunks; Claude synthesizes reference answer with citations. | Claude + SE | 40 hrs |
| 3.2 | Comparative Analysis Module | Structured comparison workflow: analyst inputs operator-claimed parameter (e.g., EUR, porosity, IP30); system retrieves comparable authoritative benchmarks; output flags material variances. | Claude + SE | 32 hrs |
| 3.3 | Source Citation & Auditability Layer | Every system output includes source attribution (document, section, date, reliability tier). Analyst can drill into source material. Full audit trail. | Claude + SE | 20 hrs |
| 3.4 | Risk Engine Integration Stub | Define and document API interface for future Risk Engine ↔ R&I Reference Engine data exchange. Implement stub endpoints. No full integration in this phase. | Claude + SE | 12 hrs |
| 3.5 | User Acceptance Testing — R&I Team | Ganlin and Ella conduct structured UAT using live Escopeta and pipeline project scenarios. Document issues and required adjustments. | Ganlin + Ella | 16 hrs |
| 3.6 | Phase 3 Milestone Review | MRB and Stan sign-off on interface, output quality, and auditability before production deployment. | MRB + Stan | 4 hrs |
| Phase 4: Hardening, Corpus Expansion & Handoff ¦ Weeks 15–20 |  |  |  |  |
| 4.1 | Corpus Expansion — Tier 2 Sources | Add secondary sources: state geological survey reports, additional basin-specific SPE papers, NoviLabs production comps, formation-level analog data. | SE + Ganlin | 24 hrs |
| 4.2 | Performance & Reliability Hardening | Load testing, latency optimization, error handling, fallback logic. Target: sub-5-second retrieval response for standard queries. | SE | 20 hrs |
| 4.3 | Corpus Governance Protocol | Document source addition/removal process, reliability tier definitions, update cadence, and version control for corpus. Enables ongoing R&I team management. | Claude + MRB | 12 hrs |
| 4.4 | Knowledge Transfer — Stan & Team | SE conducts structured KT sessions covering infrastructure, corpus management, and troubleshooting. All documentation delivered. | SE | 16 hrs |
| 4.5 | Production Launch & Baseline Documentation | Formal go-live. Baseline performance metrics documented. Post-launch support window defined (30 days). | SE + MRB | 8 hrs |

# 5. Resource Estimates & Cost

The following estimates reflect the 2678 Holdings delivery model: Claude as primary build resource, Senior SE on part-time contracting basis, internal team for review and validation.

| Resource | Estimated Effort | Estimated Cost |
| --- | --- | --- |
| Claude (application logic, prompts, code generation) | ~180 hrs equivalent | Internal / API cost |
| Senior Systems Engineer (contractor) | ~230 hrs | ~$34,500 @ $150/hr est. |
| MRB / Team (reviews, UAT, corpus curation) | ~50 hrs | Internal |
| Infrastructure (hosting, vector DB, storage, API) | Monthly opex | Est. $800–$2,000/mo |
| Total Estimated External Cost | ~230 hrs SE | ~$34,500 + ~$15,000 infra (12 mo) |

Note: SE hourly rate is illustrative at $150/hr. Final rate subject to contractor agreement. Infrastructure costs depend on corpus volume and query load; the range above reflects expected steady-state at TCA's current project pipeline scale.

# 6. Corpus Strategy — E&P Geology Domain

## 6.1  Priority Source Categories

The following source categories form the Tier 1 corpus for the initial build, prioritized for the Cotton Valley / East Texas basin context of TCA's first live use case (Escopeta Henderson County):

- USGS National Oil and Gas Assessment — formation-level resource estimates, type well data

- SPE (Society of Petroleum Engineers) — Cotton Valley formation papers, hydraulic fracturing studies, well completion analyses

- Texas Railroad Commission (RRC) — production data, well logs, completion records

- EIA — basin-level production statistics, formation-level benchmarks

- State geological surveys — Texas Bureau of Economic Geology formation characterization reports

- NoviLabs API — production analog data (subject to existing data agreement)

## 6.2  Reliability Tier Framework

All corpus documents are assigned a reliability tier at ingestion. Tier assignments are documented in the Corpus Governance Protocol (Task 4.3) and are visible to analysts in all system outputs.

- Tier 1 — Primary authoritative: U.S. government agencies (USGS, EIA), peer-reviewed SPE publications, state geological surveys

- Tier 2 — Industry standard: major operator public filings, IHS/Enverus formation benchmarks, recognized industry databases

- Tier 3 — Secondary / contextual: operator-provided analogs, regional conference presentations, news and trade press

Retrieval outputs clearly label the source tier of every citation. R&I analysts are trained to weight Tier 1 and Tier 2 sources as primary evidence; Tier 3 citations are contextual only.

# 7. Risks & Mitigations

| Risk | Level | Description | Mitigation |
| --- | --- | --- | --- |
| Source Licensing | Medium | Key authoritative sources (SPE papers, state surveys) may carry access fees or usage restrictions. | Complete source inventory and rights assessment in Phase 1 before any build commitment. |
| Retrieval Quality | Medium | RAG systems can return imprecise or off-topic chunks if chunking strategy is poorly tuned. | Phase 2 includes dedicated retrieval QA with R&I team against real query scenarios before interface build. |
| Corpus Staleness | Low–Medium | E&P reference data (production benchmarks, formation studies) ages. Outdated corpus reduces reliability. | Corpus Governance Protocol (Task 4.3) defines update cadence and source version control. |
| SE Contractor Availability | Medium | Part-time SE creates schedule dependency risk. | Front-load SE-intensive tasks; Claude handles non-infrastructure work in parallel. |
| Scope Expansion | Low | R&I team may identify additional domains (financial benchmarks, regulatory data) during UAT. | Phase 3 scope is fixed to geology/technical domain. Additional domains scoped as Phase 5. |

# 8. Success Criteria

The R&I Reference Engine will be considered successfully delivered when all of the following criteria are met:

- Corpus contains a minimum of 200 indexed Tier 1 and Tier 2 source documents covering the Cotton Valley / East Texas basin domain

- System returns relevant reference material for 90% or more of a standard R&I query set (defined during Phase 2 UAT)

- Query-to-response latency is under 5 seconds for standard geological reference queries

- All system outputs include fully traceable source citations with tier designation

- R&I analysts (Ganlin, Ella) confirm the comparative analysis module produces actionable variance flags for operator-submitted project data

- Corpus Governance Protocol is documented and Stan has completed knowledge transfer sign-off

- API integration stub is implemented and documented for future Risk Engine data exchange

# 9. Approval & Authorization

This work plan is subject to MRB approval before Phase 1 activities commence. Approval constitutes authorization to engage the Senior Systems Engineer contractor and initiate infrastructure provisioning.

Approved By:

MRB — Principal, 2678 Holdings LLC

MRB

TokenCap Advisors LLC  |  A 2678 Holdings LLC Company

TCA-WORKPLAN-2026-RI-001  |  May 2026  |  CONFIDENTIAL